WhatNext Vision Motors

Shaping the Future of Mobility with Innovation and Excellence

Planning Logic  —  Project Design Phase II

1. Project Overview

| Project Title | WhatNext Vision Motors: Shaping the Future of Mobility with Innovation and Excellence |
| --- | --- |
| Phase | Project Design Phase – II (Planning Logic) |
| Date | April 2025 |
| Team ID | WNV-2025-001 |
| Maximum Marks | 4 Marks |
| Methodology | Agile – Scrum (4 Sprints × 2 Weeks each) |
| Duration | 16 Weeks (4 Months) |
| Domain | Automotive / Electric Mobility / AI-driven Platform |

2. Team Members & Roles

| S.No | Name | Role | Key Responsibilities |
| --- | --- | --- | --- |
| 1 | MANISHA R | Team Leader | Project planning, sprint coordination, architectural decisions, client communication, milestone tracking |
| 2 | RAJKUMAR L | Backend Developer | REST API design, database schema, server-side logic, authentication, integration testing |
| 3 | TAMIZHKUMARAN M | Frontend Developer | React.js web portal, Flutter mobile app, UI/UX design, responsive layouts, API integration |
| 4 | VINITH S | ML / AI Engineer | Recommendation engine, predictive maintenance model, EV range forecasting, model deployment |
| 5 | PORSELVAN A | Cloud & DevOps Engineer | AWS infrastructure, Docker/Kubernetes, CI/CD pipelines, monitoring, security hardening |

3. Project Objectives

The following objectives define the measurable goals for WhatNext Vision Motors and are mapped to specific sprints to ensure on-time delivery:

| ID | Objective | Description | Priority | Target Sprint |
| --- | --- | --- | --- | --- |
| OBJ-01 | Build AI-Powered Vehicle Recommendation Engine | Deliver personalised vehicle suggestions based on user preferences and behaviour using ML | High | Sprint 3 |
| OBJ-02 | Develop Multi-Platform User Interface | Responsive web portal (React.js) and mobile app (Flutter) for customers, dealers and admins | High | Sprint 2 |
| OBJ-03 | Implement Real-Time EV Telemetry & Fleet Management | Live vehicle health monitoring, battery analytics and predictive maintenance alerts | High | Sprint 3 |
| OBJ-04 | Integrate Secure Payment & Booking Gateway | Seamless test-drive booking, EMI calculator and online payment via Razorpay/Stripe | Medium | Sprint 2 |
| OBJ-05 | Deploy Scalable Cloud Infrastructure on AWS | Containerised microservices on Kubernetes with auto-scaling, load balancing & 99.9% uptime | High | Sprint 4 |
| OBJ-06 | Ensure Data Security & Compliance | JWT auth, OAuth 2.0, AES-256 encryption, OWASP Top-10 compliance and AWS IAM controls | High | Sprint 4 |
| OBJ-07 | Provide Dealer & Admin Analytics Dashboard | Real-time sales insights, inventory tracking and demand forecasting dashboards | Medium | Sprint 3 |

4. Planning Methodology

4.1  Agile – Scrum Framework

The project follows the Agile Scrum methodology, divided into 4 sprints of 2 weeks each (total 16 weeks). This approach enables iterative delivery, continuous feedback, and flexibility to adapt to changing requirements in the automotive AI domain.

- Sprint Planning: MANISHA R (Team Leader) facilitates sprint planning every 2 weeks, defining sprint goals, assigning user stories and tasks

- Daily Stand-ups: 15-minute daily sync meetings for progress updates, blockers identification and cross-team coordination

- Sprint Review & Demo: End-of-sprint live demonstrations to stakeholders with working increments of the product

- Sprint Retrospective: Team reflection on process improvements after each sprint to enhance productivity

- Backlog Grooming: MANISHA R maintains and prioritises the product backlog using JIRA, refined bi-weekly with the team

4.2  Development Approach

- Frontend (React.js / Flutter): Component-driven development with reusable UI components — TAMIZHKUMARAN M

- Backend (Node.js / Express.js): RESTful API-first design with Swagger documentation — RAJKUMAR L

- AI/ML (Python / TensorFlow): Iterative model training with experiment tracking via MLflow — VINITH S

- DevOps (AWS / Docker / Kubernetes): Infrastructure-as-Code (Terraform), GitOps CI/CD — PORSELVAN A

- Version Control: Git with feature-branch workflow; Pull Requests reviewed by MANISHA R before merging to main

5. Sprint Plan (Scrum Sprints)

The project is structured into 4 Scrum sprints covering all phases from requirements to production deployment:

| Sprint | Timeline | Key Activities | Primary Owner(s) | Deliverables |
| --- | --- | --- | --- | --- |
| Sprint 1 | Wk 1–4 | Requirements, SRS, UI/UX Wireframes, Prototype, Design System | MANISHA R, TAMIZHKUMARAN M | SRS Document, Figma Prototype, Component Library |
| Sprint 2 | Wk 5–8 | Backend APIs (Auth, Vehicles, Booking), React.js Web Portal, Flutter Mobile App, Payment Integration | RAJKUMAR L, TAMIZHKUMARAN M | Backend APIs, Web Portal, Mobile App Beta |
| Sprint 3 | Wk 7–11 | AI/ML Models (Recommendation, Predictive Maintenance, EV Range), Admin Dashboard, AWS Cloud Setup | VINITH S, PORSELVAN A, TAMIZHKUMARAN M | ML Models, Dealer Dashboard, Cloud Infra |
| Sprint 4 | Wk 12–16 | System Integration, UAT, Performance/Security Testing, CI/CD, Production Deployment, Documentation | ALL MEMBERS | Live Application, Technical Docs, Final Report |

6. Work Breakdown Structure (WBS)

The WBS decomposes the entire project into 8 phases with granular tasks assigned to individual team members. Each task has a defined owner, duration, and timeline.

| WBS ID | Task / Activity | Owner | Duration | Start | End | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 | PHASE 1 – REQUIREMENTS & PLANNING |  |  |  |  |  |
| 1.1 | Stakeholder requirements gathering & BRD | MANISHA R | 3 days | Wk 1 | Wk 1 | Not Started |
| 1.2 | System requirement specification (SRS) | MANISHA R | 3 days | Wk 1 | Wk 2 | Not Started |
| 1.3 | Technology stack finalisation | MANISHA R / ALL | 2 days | Wk 2 | Wk 2 | Not Started |
| 1.4 | Project schedule & sprint planning | MANISHA R | 1 day | Wk 2 | Wk 2 | Not Started |
| 2.0 | PHASE 2 – UI/UX DESIGN & PROTOTYPING |  |  |  |  |  |
| 2.1 | Wireframes – Web portal & Mobile App | TAMIZHKUMARAN M | 4 days | Wk 3 | Wk 3 | Not Started |
| 2.2 | High-fidelity Figma prototype | TAMIZHKUMARAN M | 3 days | Wk 3 | Wk 4 | Not Started |
| 2.3 | UI design system & component library | TAMIZHKUMARAN M | 3 days | Wk 4 | Wk 4 | Not Started |
| 2.4 | Design review & stakeholder sign-off | MANISHA R | 1 day | Wk 4 | Wk 4 | Not Started |
| 3.0 | PHASE 3 – BACKEND & DATABASE DEVELOPMENT |  |  |  |  |  |
| 3.1 | Database schema design (PostgreSQL / MongoDB) | RAJKUMAR L | 3 days | Wk 5 | Wk 5 | Not Started |
| 3.2 | User auth API (JWT, OAuth 2.0) | RAJKUMAR L | 4 days | Wk 5 | Wk 6 | Not Started |
| 3.3 | Vehicle management & inventory API | RAJKUMAR L | 5 days | Wk 6 | Wk 7 | Not Started |
| 3.4 | Booking, CRM & payment integration (Razorpay) | RAJKUMAR L | 5 days | Wk 7 | Wk 8 | Not Started |
| 3.5 | Unit & integration testing – backend | RAJKUMAR L | 3 days | Wk 8 | Wk 8 | Not Started |
| 4.0 | PHASE 4 – FRONTEND DEVELOPMENT |  |  |  |  |  |
| 4.1 | React.js web portal – customer module | TAMIZHKUMARAN M | 5 days | Wk 5 | Wk 6 | Not Started |
| 4.2 | React.js web portal – dealer & admin dashboard | TAMIZHKUMARAN M | 5 days | Wk 6 | Wk 7 | Not Started |
| 4.3 | Flutter mobile app (iOS & Android) | TAMIZHKUMARAN M | 5 days | Wk 7 | Wk 8 | Not Started |
| 4.4 | Frontend-backend API integration & testing | TAMIZHKUMARAN M | 3 days | Wk 8 | Wk 8 | Not Started |
| 5.0 | PHASE 5 – AI / ML DEVELOPMENT |  |  |  |  |  |
| 5.1 | Data collection & preprocessing pipeline | VINITH S | 4 days | Wk 7 | Wk 7 | Not Started |
| 5.2 | Vehicle recommendation model (Scikit-learn) | VINITH S | 5 days | Wk 8 | Wk 9 | Not Started |
| 5.3 | Predictive maintenance model (TensorFlow) | VINITH S | 5 days | Wk 9 | Wk 10 | Not Started |
| 5.4 | EV range forecasting model & API (FastAPI) | VINITH S | 4 days | Wk 10 | Wk 10 | Not Started |
| 6.0 | PHASE 6 – CLOUD & DEVOPS SETUP |  |  |  |  |  |
| 6.1 | AWS infrastructure setup (EC2, RDS, S3, EKS) | PORSELVAN A | 4 days | Wk 9 | Wk 9 | Not Started |
| 6.2 | Docker containerisation of all services | PORSELVAN A | 3 days | Wk 9 | Wk 10 | Not Started |
| 6.3 | Kubernetes deployment & auto-scaling config | PORSELVAN A | 4 days | Wk 10 | Wk 10 | Not Started |
| 6.4 | CI/CD pipeline (GitHub Actions / AWS CodePipeline) | PORSELVAN A | 3 days | Wk 11 | Wk 11 | Not Started |
| 6.5 | Security hardening, monitoring & alerts | PORSELVAN A | 3 days | Wk 11 | Wk 11 | Not Started |
| 7.0 | PHASE 7 – SYSTEM INTEGRATION & TESTING |  |  |  |  |  |
| 7.1 | End-to-end system integration testing | MANISHA R / ALL | 4 days | Wk 12 | Wk 12 | Not Started |
| 7.2 | Performance & load testing (JMeter) | PORSELVAN A | 3 days | Wk 12 | Wk 13 | Not Started |
| 7.3 | Security penetration testing | PORSELVAN A | 3 days | Wk 13 | Wk 13 | Not Started |
| 7.4 | User acceptance testing (UAT) | MANISHA R | 3 days | Wk 13 | Wk 13 | Not Started |
| 8.0 | PHASE 8 – DEPLOYMENT & DOCUMENTATION |  |  |  |  |  |
| 8.1 | Production deployment on AWS | PORSELVAN A | 2 days | Wk 14 | Wk 14 | Not Started |
| 8.2 | Technical documentation & API docs (Swagger) | RAJKUMAR L | 3 days | Wk 14 | Wk 15 | Not Started |
| 8.3 | User manual & training material | TAMIZHKUMARAN M | 3 days | Wk 15 | Wk 15 | Not Started |
| 8.4 | Final project report & presentation | MANISHA R / ALL | 5 days | Wk 15 | Wk 16 | Not Started |
| 8.5 | Project review, submission & handover | MANISHA R | 2 days | Wk 16 | Wk 16 | Not Started |

7. Project Milestones & Deliverables

The following 10 milestones track the progress of the project across the 16-week timeline:

| ID | Milestone | Target Date | Responsible | Deliverable |
| --- | --- | --- | --- | --- |
| M-01 | Requirements & SRS Approved | End of Week 2 | MANISHA R | SRS Document |
| M-02 | UI/UX Prototype Signed Off | End of Week 4 | TAMIZHKUMARAN M | Figma Prototype |
| M-03 | Backend APIs Complete & Tested | End of Week 8 | RAJKUMAR L | API Documentation |
| M-04 | Frontend (Web + Mobile) Complete | End of Week 8 | TAMIZHKUMARAN M | Web Portal + App Build |
| M-05 | AI/ML Models Deployed | End of Week 10 | VINITH S | ML Model Endpoints |
| M-06 | Cloud Infrastructure Live | End of Week 11 | PORSELVAN A | AWS Deployment Report |
| M-07 | UAT Completed & Signed Off | End of Week 13 | MANISHA R | UAT Sign-off Sheet |
| M-08 | Production Deployment | End of Week 14 | PORSELVAN A | Live Application URL |
| M-09 | Final Documentation Submitted | End of Week 15 | ALL MEMBERS | Technical Docs, User Manual |
| M-10 | Project Review & Final Submission | End of Week 16 | MANISHA R | Final Report + Presentation |

8. Resource Allocation Plan

Each team member is allocated 100% to the project during their active sprints. The table below outlines individual responsibilities, tools, and engagement periods:

| Member | Role | Assigned Work | Active Sprints | Allocation | Tools / Technologies |
| --- | --- | --- | --- | --- | --- |
| MANISHA R | Team Leader | Planning, Review, Coordination | Sprint 1–4 | 100% | Project Tracker, MS Teams, JIRA |
| RAJKUMAR L | Backend Developer | Backend APIs, DB, Integrations | Sprint 2–4 | 100% | VS Code, Postman, PostgreSQL, MongoDB, GitHub |
| TAMIZHKUMARAN M | Frontend Developer | Web, Mobile, UI/UX | Sprint 1–4 | 100% | Figma, React.js, Flutter, VS Code, GitHub |
| VINITH S | ML / AI Engineer | ML Models, Data Pipeline | Sprint 3–4 | 100% | Python, TensorFlow, Scikit-learn, Jupyter, FastAPI |
| PORSELVAN A | Cloud & DevOps Engineer | AWS, Docker, CI/CD, Security | Sprint 3–4 | 100% | AWS Console, Docker, Kubernetes, GitHub Actions |

9. Risk Register & Mitigation Plan

The following risks have been identified for WhatNext Vision Motors. Each risk has a designated owner and mitigation strategy to minimise project impact:

| ID | Risk | Description | Likelihood | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Scope Creep | Feature additions mid-project | High | Medium | Strict change control process; MANISHA R approves all scope changes | MANISHA R |
| R-02 | API Integration Delay | Third-party APIs (Maps, Razorpay) unavailable or changed | Medium | Medium | Maintain mock API layer; integrate early in Sprint 2 | RAJKUMAR L |
| R-03 | ML Model Accuracy | AI recommendations below acceptable threshold | Medium | High | Iterative training with larger datasets; fallback rule-based engine | VINITH S |
| R-04 | Cloud Cost Overrun | AWS costs exceed budget | Low | High | Use AWS Free Tier + Cost Explorer alerts; right-size instances | PORSELVAN A |
| R-05 | Security Breach | Unauthorised data access | Low | High | Penetration testing in Sprint 4; OWASP compliance; AWS WAF | PORSELVAN A |
| R-06 | Team Member Unavailability | Member falls ill / unavailable | Medium | Medium | Cross-training; task documentation; MANISHA R re-assigns tasks | MANISHA R |
| R-07 | Performance Issues | Slow response under high load | Medium | Medium | Redis caching, CDN, load testing with JMeter in Sprint 4 | PORSELVAN A |

10. Communication Plan

10.1  Internal Communication

- Daily Stand-up Meetings: Every weekday at 9:00 AM — 15 minutes via MS Teams / Google Meet (All Members)

- Sprint Planning & Review: Every 2 weeks, 2-hour session led by MANISHA R

- Instant Messaging: WhatsApp / Slack channel for real-time team communication

- Task Tracking: JIRA board maintained by MANISHA R — all members update task status daily

- Code Reviews: GitHub Pull Requests — reviewed by MANISHA R and respective module lead before merging

10.2  Reporting & Documentation

- Weekly Status Report: MANISHA R prepares a 1-page status update every Friday summarising progress, blockers and next steps

- Sprint Report: Delivered at the end of each sprint — includes velocity, burn-down chart, completed stories and risks

- Technical Documentation: Maintained in Confluence / GitHub Wiki by respective module owners throughout development

- API Documentation: Auto-generated via Swagger/OpenAPI — maintained by RAJKUMAR L

11. Quality Assurance Plan

- Code Quality: ESLint (JavaScript) and Pylint (Python) enforced in CI pipeline — no merge without passing lint checks

- Unit Testing: Minimum 80% code coverage using Jest (Frontend) and PyTest (Backend/ML) — RAJKUMAR L & VINITH S

- Integration Testing: API integration tests using Postman/Newman automated in CI/CD — RAJKUMAR L

- Performance Testing: Load testing with Apache JMeter — target <200ms API response at 500 concurrent users — PORSELVAN A

- Security Testing: OWASP ZAP penetration testing, AWS Security Hub compliance scan — PORSELVAN A

- UAT: User Acceptance Testing with stakeholder scenarios in Sprint 4 — sign-off required before production — MANISHA R

- ML Model Validation: Minimum 85% accuracy threshold for recommendation engine; RMSE-based evaluation for EV range model — VINITH S

12. References

https://www.scrum.org/resources/scrum-guide — Official Scrum Guide

https://www.pmi.org — Project Management Institute (PMI) Standards

https://aws.amazon.com/architecture — AWS Well-Architected Framework

https://jira.atlassian.com — Agile project tracking with JIRA

https://c4model.com — C4 Architecture Model

https://owasp.org/www-project-top-ten — OWASP Top Ten Security Standards